## Action Plan Template
Name of your co-leadership group: | INSERT HERE PLEASE
Action Area / Idea | Strategic / Framework Alignment | Lead Organisation/Person | Resources Required | Milestones & Timeline | Success Measures
Rubies female empowerment one to one mentoring to secondary aged pupils struggling with confidence and self esteem impacting their attendance | Responsive targeted support’ | Rubies mentoring to females in secondary | 8 p/t mentors, cost? | three years subject to funding | 30 girls per year supported with wellbeing
Achieve mentors giving trusted adult to young people yr7-9 who are struggling to engage in education | Responsive targeted support’ | Achieve | ?? Alan?? | ?? | ??
Wellbeing and resilience coaching for young people identified as at risk of disengaging from Y10 upwards, who may struggle with transition that need intensive 6 month one to one support. Support delivered in the community | Responsive targeted support’ | Turning Tides - Bridges Outcome Partnership | 1f/t coach, £35k | one year | 30 young people per year supported by their wellbeing
Peer mentoring to support transition from Y6 to Y7 | Responsive targeted support’ | Headstarters educational pathway | School identigy children who act as mental health champions. They deliver assemblies to Y6 to support transition. Andy? | ??Andy
Activities delivered over the summer to Y6 identified as potential to struggle with transition | Responsive targeted support’ | Headstar and HAF | Andy? | ??Andy
Spotlight Effective Wellbeing Practices that Drive Improved Attendance | Embedding live experience and co-production | Bridges Outcomes Partnership | 1 data analyst, programme manager, coach, mentor, young people for co-production | Report in Y2 to spotlight best practice informed by co-production | Disseminated across secondary education settings to enhance the impact of asset-based approaches in improving student attendance.
Strengthen Staff Capability via Trauma-attuned Approaches | Strengthening systems | ?? | Training for coaches | Y1 training completed by all coaches and mentors | Increased wellbeing in YP/coproduced best practice on trauma attuned support and advocacy
Apply Proven Approaches from Barnardo’s to Strengthen Wellbeing Interventions | Responsive targeted support’ | Bridges Outcomes Partnership | Review and share learnings from Barnardos reporting. Seek input from Headstart on best practice for coaching/mentoring | Implement best practice across delivery | Development of policies and codes of practice guided by insights

## How to prioritise actions
Looking at the Framework actions and ideas generated in the solutions pack seek to identify no more than 4 'quick wins' and 1 'major strategic focus' action for your plan
This will help us (across the co-leadership thematic groups) identify High Impact – Low Effort (quick wins) and High-Impact-High Effort (major strategic focus) actions
To make sure you think you've got achievable actions consider using 'RAFT' as a means of discussing the ones you've prioritised and sharpen them accordingly.
The co-leadership group felt familiar with setting objectives that are SMART so oyu may like to use that approach too in your selection process
Specific
Measurable
Achieveable
Realistic
Timebound

## Success - outcomes
Making Attendance Everyone's Business - success measures: you could consider inserting some of these outcomes in your action plan
Here are the outcomes that alliance members across the system believe we should be seeking to improve together through co-ordinated efforts.
For full details see the Project's survey results here: | https://www.skyblue.org.uk/attendance/perceptions.html