## Action Plan Template
Name of your co-leadership group: | Relational Practice
Action Area / Idea | Strategic / Framework Alignment | Lead Organisation/Person | Resources Required | Milestones & Timeline | Success Measures
Relational Practice and policy & practice | All pillars cross- cutting theme | RCBC / Mo Mowlam Academy |  | 2029-07-01 | Relational practice fully embedded in one secondary and one primary school in R&C, advocating for the expansion to others by July 2029 Staff, pupils and parents feel a greater sense of belonging at the end of the academic year July 2027, than they did in July 2026 (belonging questionnaire)
Review Devon educational model, alongside wider practice models- do we feel this this could be adopted in R&C |  | RG, JS, MD | Time from Ed Psychologist, VS, Head Teacher & SW Academy | Document reviewed and feedback collated by August 2025
How well has the Devon policy and practice been embedded in secondary schools / how have CYP and families been involved? |  | AO & JS | Time from partners | Meet with Devon CC / September 2025
Define what R&C educational relational model is / aligned C&F Relational Practice Model |  | AO, RG, JS & MD | Wider working / focus group / funding for DCC to support work | Support from DCC - January 2026
Identify a school/s willing to potentially adopt the policy and practice |  | AO, RG, JS & MD | Time from partners | EOI out to schools by March 2026
Identify 2 trailblazer schools for pilot |  | AO, RG, JS & MD | Would be determined through development of model | 2 schools identified by April 2026

## How to prioritise actions
Looking at the Framework actions and ideas generated in the solutions pack seek to identify no more than 4 'quick wins' and 1 'major strategic focus' action for your plan
This will help us (across the co-leadership thematic groups) identify High Impact – Low Effort (quick wins) and High-Impact-High Effort (major strategic focus) actions
To make sure you think you've got achievable actions consider using 'RAFT' as a means of discussing the ones you've prioritised and sharpen them accordingly.
The co-leadership group felt familiar with setting objectives that are SMART so oyu may like to use that approach too in your selection process
Specific
Measurable
Achieveable
Realistic
Timebound

## Success - outcomes
Making Attendance Everyone's Business - success measures: you could consider inserting some of these outcomes in your action plan
Here are the outcomes that alliance members across the system believe we should be seeking to improve together through co-ordinated efforts.
For full details see the Project's survey results here: | https://www.skyblue.org.uk/attendance/perceptions.html