## Action Plan Template
Name of your co-leadership group: | Targeted Support and Caseload Management Solutions
Action Area / Idea | Strategic / Framework Alignment | Lead Organisation/Person | Resources Required | Milestones & Timeline | Success Measures
Establish a way, using data available, for schools to predict the children and young people who may need targeted support to improve their attendance, especially to support transitions from year 6 to year 7. | Pillars 3 and 4 | Local Authority (Education Team) | Intelligence team time to review Vulnerable/Valuable list and the Yr6 Transtions spreadsheet. | Review Valuable/Vulnerable list to consider including YJB data over summer 2025. Merge this with the Y6 transition spreadsheet that is issued to Secondary Schools at Easter every year by March 2026. | Year 6 pupils can be identified for additional support with transition into Secondary School and the receiving school understands their individual circumstances as well as their trauma and/or any barriers tro attendance.
Investigate and evaluate the impact of using professional 'triage' meetings in Secondary Schools to identify pupils of concern earlier so we can take a whole family/early support approach to improve their attendance. This to include investigating use of the vulnerable/valuable list issued termly to DSLs (do attendance leads in school see or know about this list?) | Pillars 3 and 4 | Beth from St Peters/Nicola Hall RCBC Early Help | Time for Beth and N Hall to investgate this appraoch more through discussions with those using it already. | Investigate use of triage model locally (e.g. Laurence Jackson) and in Middlesbrough over summer 2025. | A potential model for a place-based virtual team around the school triage process is developed to pilot later in year.
Trial a place-based school approach to early identification for targeted support if above evaluates well. | Pillars 3,4 and 5. | Beth from St Peters/Nicola Hall RCBC Early Help plus one more school (Normanby Outwood?) | LA Officer from children's services would attend the termly triage meetings alongside YJB rep, school attendance lead, Inclusion officer, Careers, School Nurse, SEND Officer to identify and RAG rate pupils whose attendance is falling/of concern. Linked EHCs to support the school leads to complete Our Family Plans to coordinate further support and an action plan for the children/families causing most concern, so that all professionals involved can work together as a Team Around the Family to improve attendance. | Autumn term 2025 - place-based pilot in St Peters and another secondary school. | Children and families circumstances are understood, tailored support is put in place earlier (prior to PIP) and attendance improves for those targeted.
Upskilling school-based staff to give them the confidence to be the lead practitioner in terms of coordinating early support plans (Our Family Plans) | Pillars 3,4 and 5. |  |  |  | DSLs/Pastoral staff have the skills needed to provide consistent level of support at the earliest stage and unpick what may be happening for the whole family that may be contributing to poor attendance fo the child/young person.
Consider reviewing attendance procedures to insist on attendance welfare service or schools completing an Our Family Plan and TAF approach, prior to going into Court for attendance proceedings, to help families before they reach that crisis point. | Pillars 3,4 and 5.

## How to prioritise actions
Looking at the Framework actions and ideas generated in the solutions pack seek to identify no more than 4 'quick wins' and 1 'major strategic focus' action for your plan
This will help us (across the co-leadership thematic groups) identify High Impact – Low Effort (quick wins) and High-Impact-High Effort (major strategic focus) actions
To make sure you think you've got achievable actions consider using 'RAFT' as a means of discussing the ones you've prioritised and sharpen them accordingly.
The co-leadership group felt familiar with setting objectives that are SMART so oyu may like to use that approach too in your selection process
Specific
Measurable
Achieveable
Realistic
Timebound

## Success - outcomes
Making Attendance Everyone's Business - success measures: you could consider inserting some of these outcomes in your action plan
Here are the outcomes that alliance members across the system believe we should be seeking to improve together through co-ordinated efforts.
For full details see the Project's survey results here: | https://www.skyblue.org.uk/attendance/perceptions.html